MANAGEMENT PLAN

PROJECT: BIOENERGY CONTRIBUTION OF LATIN AMERICA, CARIBBEAN AND AFRICA TO THE GSB PROJECT - LACAf-Cane-I

Coordination: Luís Augusto Barbosa Cortez

Institution: NIPE/Unicamp

Brazilian Partners: CTBE, Icone, CTC, ESALQ/USP, CGEE, Embrapa, IRN/Unifei

Foreign Partners: GSB Project, IANAS, ISBUC, Imperial College, ERcane, SU, CEEEZ

Financing Institution: FAPESP

Abstract project:

Modern and sustainable bioenergy production may be an effective way to substitute substantial portions of energy demand for transportation in the future. Since the overall scale of bioenergy production will in part depend on the availability of fertile land with good climatic conditions, it is clear that, if food production is to be increased to meet future needs and biodiversity protected, basically the world will consider the Latin America & Caribbean and Africa continents for future expansion of bioenergy. The LACAf-Cane-I project will, therefore, focus in these two continents, to evaluate the prospects of sustainable bioethanol production from sugarcane. Bioelectricity production from sugarcane will also be considered due to its important impacts on rural development and its synergy with ethanol production. This project is a contribution of Latin America, the Caribbean and Africa to the GSB project. This project has concluded its first phase, promoting five continental conventions during 2010. The main information on the GSB project and the conventions outcome are summarized at http://engineering.dartmouth.edu/gsbproject/.  The full text of the Latin America (São Paulo) and Africa (Stellenbosh, South Africa) continental conventions may be found in the Annex and the remaining resolutions are also available on line. The LACAF-Cane-I project aims to contribute to the next stages of the GSB project focusing Latin America, the Caribbean and Africa, focusing on sugarcane and other energy complementary crops, that have already presented effective achievements or have indicated good potential in wet tropical zones. This feedstock will be assessed for bioenergy taking into account two energy vectors: bioethanol (for gasoline substitution) and bioelectricity, both using advanced first and second generation technologies.

Main activities LACAF I  and LACAfs projects

The detailed overall project LACAF I was presented by management plan sent to FAPESP. Request of FAPESP below will show up with adherents activities related to LACAf I, as well as relations between complementarity between future projects LACAfs being prepared (see Figure 1). Management Plan LACAF I, demonstrate the initial presentation of the project, as well as the coordination of its subprojects, showing how the products of the various subprojects LACAf I are connected and realigned in activities under this and future LACAFs. For example, studies of land use (subproject 2) provide a better basis for projecting the potential supply of biofuel (subproject 1), as well as provide elements for the assessment of productive configurations (subproject 3). This relationship explains this by their importance in the objectives of the Project LACAf I especially within the countries to be studied (see Figure 2).

Figure 1

Month 2      Month 3                       Month 9    Month 10           Month 12           Month 16         Month 17             Month 18            Month 20  Month 24

↓            ↓                   ↓           ↓                    ↓      ↓                ↓                    ↓                 ↓               ↓

| SP1 Diagnosis (Horta) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SP2a Survey CTC (Beauclair) |  |  |  |  |  |  |  |  |  |
| SP2b Survey Icone (Beauclair) |  |  |  |  |  |  |  |  |  |
| SP2c Determining Land Use and Physical Near-Term Potential (Beauclair) |  |  |  |  |  |  |  |  |  |
| SP3 Productive Model (Regis) |  |  |  |  |  |  |  |  |  |
| Conclusions |  |  |  |  |  |  |  |  |  |

↑              ↑                            ↑               ↑                    ↑                   ↑                     ↑                   ↑                    ↑                 ↑

1st Meeting    2nd Meeting       3rd Meeting          4th Meeting       5th Meeting                   6th Meeting           7th Meeting      8th Meeting

Campinas          Campinas                Calli, CO        Campinas            Durban, AS                                       Campinas               Campinas          Campinas

Figure 2

The plan proposed Project LACAf will considering assess the conditions in which the production of bioenergy for sustainable base can and should be promoted, and we consider the target groups most relevant:

a) the academic community in Brazil and abroad, highlighting the paths taken and the results already established, as well as the new challenges that have to be explored, and

b) decision makers and stakeholders in the field of energy, environmental and agribusiness (producers of raw materials, manufacturing plants and suppliers of goods and services), including international agencies, especially the brazilian experience, and state of São Paulo in particular, and the possibilities, advantages and implications of their adaptation to the contexts studied in this project. This direction will be prepared articles to be sent to scientific journals.

Subproject 1 (SP1)

Title: Regional diagnosis in Latin America & Caribbean and Africa & Integrated analysis

Coordination: Luiz Augusto Horta Nogueira

Introduction: The goal of the LACAF-I Project is to create a robust and updated perspective for sugarcane bioenergy development in the targeted countries, aiming to build a base for consistent decision making and offering a possible model for similar contexts. It is relevant to observe that initially literature based data will be used to draw a basic framework and a set of preliminary conclusions, to be further improved with data and complementary information from other LACAF studies, for instance on soil, water resources and pasture intensification.

Objectives: As an introductory approach to the bioenergy questions, LACAf-Cane-I task Diagnosis of Energy and Food Situation in LA and AF & Integrated analysis will address fundamental aspects (environmental, social, technological, economic and institutional), taking into account the current situation and highlighting the most evident trends, in order to assess the current context to promote sustainably bioenergy from sugarcane.

Schedule Phases and Tasks: To set and organize the basic phases in an action program. Each phase should start with a specific plan setting, with clear definitions of intermediate activities and should be closed with a partial report, presenting the relevant information gathered and conclusions achieved. Periodic internal meetings and more open workshops should be done.

| Phases | Tasks | Team | Duration | Products |
| --- | --- | --- | --- | --- |
| I |  |  |  |  |
| Collect and organize data on economy, population, energy, agriculture, etc. for Africa and Latin America and the Caribbean countries, using UN agencies and similar institutions as source of information, presenting a general perspective for each region and highlighting the more relevant aspects. | I.1 Workshops on project approach – kick-off I.2 Literature prospecting and methodology discussion I.3 Choice overall indicators - data prospecting I.4 Comparative analyses on diagnosis in Latin America,Caribbean and Africa I.5 Evaluate diagnosis and integrated analysis I.6 Workshops on project approach – visiting countries feedback | Horta Pós-doc (2), Mauro, Manduca, Rubens Rincon, Emile, Kafarov, Jean Claude, Annie, Francis Y, Laurent, Frank, Leonard | 2 months 4 months 4 months 1 month 1 month 1 month | a. Report Data base b. Report Workshop |
| II |  |  |  |  |
| For the selected countries (Colombia, Guatemala, Mozambique and South Africa), prepare a detailed database in these aspects, presenting the evolution, current situation and perspectives of: | II.1.Economy: GNP evolution and composition, agricultural commodities participation and trends in national trade, staple food export and import, financing conditions. II.2.Energy: national energy matrix evolution and trends, energy prices and costs (mainly for liquid fuels and electricity), vehicular fuels demand and market structure, light vehicles fleet (number and age), energy dependence situation and concerns, regulatory framework and decision making processes. II.3.Agriculture and agro-industry (with emphasis in sugarcane and sugarcane products): planted area, production, domestic demand, prices and estimated costs of main agricultural products, total arable land, irrigation requirements, agricultural inputs market, institutional aspects, research activities and resources, management and financing issues. II.4 Environmental issues: general appraisal of near-term potential and perspectives of increase bioenergy production, legislation (including fuel specs and emission limits), institutions and decision making processes. II.5 Social aspects: employment and wages indicators (rural and urban), HDI evolution and trends, public perception on biofuels programs. II.6 Know-how in renewable energy, bioenergy and biofuels: outputs and lessons from previous experiences, projects and programs, human resources (technical and university levels), equipment industry situation and perspectives. | Horta Pós-doc (2), Mauro, Manduca, Rincon, Emile, Kafarov, Annie, Frank, Leonard | 2 months 3 months 6 months 6 months 4 months 3 months 12 months | c. Report I d. Report II e. Report Workshop |
| III |  |  |  |  |
| Define a preliminary potential of ethanol production, taking into account the data obtained in the previous phase and considering two basic scenarios: a) to keep the current status of sugarcane agroindustry and use the available molasses and a marginal increment in sugarcane productivity and b) to expand the sugarcane production, under the constraints evaluated before. | III.1 Comparative analysis on regional potential of ethanol production III.2 Analysis on model sustainability indicators III.3 Workshops on project approach – team’s feedback III.4 Available preliminary results | Horta Pós-doc (2), Mauro, Emile, Kafarov, Annie, Frank, Leonard | 4 months 3 months 1 month 1 months | f. Report III |
| IV |  |  |  |  |
| Forecast the domestic ethanol demand, considering the fleet actual composition and evolution, and two basic scenarios: a) an E10 blending program and b) a pure hydrous ethanol flex fuel vehicle introduction. | IV.1 Forecast by country Latin America IV.2 Forecast by country Caribbean IV.3 Forecast by country Africa (Mozambique and South Africa) | Horta Pós-doc (2), Mauro, Manduca, Rincon, Emile, Kafarov, Annie, Frank, | 3 months 3 months 3 months | g. Report IV h. Report V i. Report VI |
| V |  |  |  |  |
| Evaluate the perspective of an national ethanol program introduction, based on the preceding phases and taking into account also the institutional perspective and other constraints and drives. | V. 1 Comparative countries and integrated analysis V. 2 Workshop | Horta Pós-doc (2), Rincon, Emile, Frank, | 6 months 1 month | j. Report VII k. Report Workshop |
| VI |  |  |  |  |
| Develop a preliminary assessment of the benefits and impacts of ethanol production and use, in energy, social, economic and environmental terms. | VI.1 Full analysis: Assessment impacts ethanol production in energy, social, economic and environment for country: Guatemala, Mozambique, South Africa, Brazil and Colombia. | Horta Pós-doc (2), Mauro, Manduca, Rubens Rincon, Emile, Kafarov, Jean Claude, Annie, Francis Y, Laurent, Frank, Leonard | 12 months | l. Report VIII |
| VII |  |  |  |  |
| Prepare an initial list of topics to be dealt aiming to improve the bases for an ethanol program planning and implementation. | VII.1 Workshop VII.2 Full analysis about ethanol program implementation. | Horta Pós-doc (2), Mauro, Manduca, Rubens Rincon, Emile, Kafarov, Jean Claude, Annie, Francis Y, Laurent, Frank, Leonard | 1 month | m. Report Workshop n. Report IX |
| VIII |  |  |  |  |
| Prepare papers reporting, at regional perspective and at country level, the achievements and conclusions, directed to: a) decision makers, with the main aspects and more relevant conclusions and recommendations and b) researchers, with a more detailed discussion on methodology and data used and produced. | VIII.1 Workshop general VIII.2 Paper position | Horta Pós-doc (2), Mauro, Manduca, Rubens Rincon, Emile, Kafarov, Jean Claude, Annie, Francis Y, Laurent, Frank, Leonard, | 6 months | o. Report Workshop p. Papers |

Subproject II (SP2)

Title: Determining Land Use and Physical Near-Term Potential for Bioenergy Production in Latin America and Africa

Coordination: Edgar Beauclair

Introduction: Any project of expansion or introduction of a crop in a country or region need to be linked with deep studies in areas such as the environment (weather and soil)  to define the sustainable crop production potential. Inside this concept, the growth of bioethanol in the world will demand those studies that will be the basis for future taking decisions inside the bioenergy sector.

Objectives: The main objective of this analysis is to assess the land use impacts of biofuels production in Latin America and Africa. The specific objectives of this study are build a base map of land cover; analyze recent land use dynamics and identify a pattern of land use change; simulate land use change according to biofuel production scenarios; evaluate potential GHG emissions due to land use change; identify potential areas to sugarcane production in African and Latin American countries; and quantify the different production potential of sugarcane crops in these countries and  modeling a crop to estimate final production. A better approach for strategic planning goals are edaphoclimatic models that use parameters that are commonly obtained like type of soil, including its water retention capacity for an accurate hydric balance, historical series of whether records, specially rain and temperature and of course, some crop productivity under these conditions. Since in all cases the exact value of the parameters, the general model based on the theory of a system that converts the total amount of mass (water) and energy (temperature – degree-days) received into a productivity of the crop from that system. Much different conversion efficiency will be found and validation studies must be taken.

Schedule Phases and Tasks: To set and organize the basic phases in an action program. Each phase should start with a specific plan setting, with clear definitions of intermediate activities and should be closed with a partial report, presenting the relevant information gathered and conclusions achieved. Periodic internal meetings and more open workshops should be done.

Subproject II.a: CTC: Sugarcane Production near-term Potential

| Action | 1st year |  |  |  | 2nd year |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1st trim. | 2nd trim. | 3rd trim. | 4th trim. | 1st trim. | 2nd trim. | 3rd trim. | 4th trim. |
| Evaluations of areas and obtain data |  |  |  |  |  |  |  |  |
| Creation of basic maps |  |  |  |  |  |  |  |  |
| Field trips |  |  |  |  |  |  |  |  |
| Creation of production near-term potential maps |  |  |  |  |  |  |  |  |
| Preparation of reports |  |  |  |  |  |  |  |  |
| Final Report |  |  |  |  |  |  |  |  |

Subproject II.b : ICONE: Land Use Change in Latin America and Africa

|  | 1 st | 2 st | 3 st | 4 st | 5 st | 6 st |
| --- | --- | --- | --- | --- | --- | --- |
| Step 1 |  |  |  |  |  |  |
| Step 2 |  |  |  |  |  |  |
| Step 3 |  |  |  |  |  |  |
| Step 4 |  |  |  |  |  |  |
| Final report |  |  |  |  |  |  |

The beginning of this step depends on CTC finishes the potential study. It has to be decided also the production scenario for each country.

Subproject II.c : ESALQ: Use a Sugarcane Crop Model and Estimate Total Sugarcane Ethanol Production in LA and AF

| Phases | Tasks | Team | Duration | Products |
| --- | --- | --- | --- | --- |
| I |  |  |  |  |
| Identify the potential area to plant sugarcane based on climate and soil conditions | I.1 Evaluation of the areas and obtain the data I.2 Creation of basic maps I.3 Field trips I.4 Creation of production near-term potential maps | Fernando e Felipe (CTC) Posdoc (1) | 3 months 9 months 12 months 2 months | Data-reports Maps Maps and reports Maps and final report |
| II |  |  |  |  |
| To establish the constrains based on environmental conditions (preservation areas) | II.1 Build a base map of land cover II.2 Analyze recent land use dynamics and identify a pattern of land use change II.3 Simulate land use change according to biofuel production scenarios II.4 Evaluate potential GHG emissions due to land use change | André Nassar Marcelo Moreira Posdoc (1) | 16 months 16 months 8 months 8 months | Maps and report Report Report Report |
| III |  |  |  |  |
| To development yield model to estimate the potential biomass production | III.1 to Built the model III.2 to test the model III.3 to validate the model | Edgar Beauclair Rubens Posdoc (1) | 16 months 8 months 8 months | Model Report Final model |

Subproject III (SPIII)

Title: Productive Models & Innovation Studies

Coordination: Manoel Regis Lima Verde Leal

Introduction: The introduction or expansion of the sugarcane ethanol production in a developing country, in particular in Latina America and Africa, has to be preceded by a careful analysis of the local conditions, especially concerning the main sustainability issues of the three columns: Economic, Environmental and Social. This analysis should lead to one or more production models adapted to the political, regulatory, technical and cultural particularities of each country. In the development of the project of a new sugarcane ethanol distillery, the industrial sector can be installed already using the state of the art of the technology for cane processing to ethanol and energy generation. However, the agricultural sector has to follow the common practices in the initial stages, although it is highly desirable to have a program of progressive improvements and modernization, compatible with the farms skills and the ability of the government and private investors to introduce new and more efficient technologies. The goal of the LACAF-Cane-I project is to create a robust and updated perspective for sugarcane bioenergy development in the targeted countries, aiming to build a base for consistent decision making and offering a possible model for similar contexts. While the industrial sector of the production path, the distillery itself, can be built using the state of the art technology already in use elsewhere for cane processing, the agricultural sector has to be adapted to the existing agricultural practices at the initial stages and progressively introduce the improvements and modernization with an associate capacity building program in the region or country. This process should be compatible with the existing famers skills and the ability of the government and private sector to introduce and support more efficient technologies and, mainly, best agricultural practices. Any tentative to make radical changes in the local agriculture culture and practices will have a high chance of failure due to the conservative and suspicious nature of the traditional farmers in developing countries. It must be demonstrated that there will be advantages to the local community in terms of job creation, increase in wealth, improvement of the regional infrastructure and access to energy services. Nevertheless, to be successful in the long term the feedstock production for bioenergy have has to follow the most efficient and sustainable practices since it has to fulfill certain requirements not normally demanded for food production. Energy efficiency, low lifecycle greenhouse gas (GHG) emissions, high yields, low production costs, care about soil and water quality, social impacts are some of the items that will deserve a careful assessment.

Objectives: The objective of this subproject III is to determine the most important items and the corresponding road map that will conduct the sugarcane ethanol production technologies from the present stage to a desired stage of performance, bearing in mind the specificities of each country under consideration.

Schedule Phases and Tasks: To set and organize the basic phases in an action program. Each phase should start with a specific plan setting, with clear definitions of intermediate activities and should be closed with a partial report, presenting the relevant information gathered and conclusions achieved. Periodic internal meetings and more open workshops should be done. The so called optimum model is just a conceptual framework of the interactions between the main stakeholders that will be used as a guide to the assembly of the production model alternatives by changing the priorities of the driving forces and stakeholder interests. The main driving forces to be considered are: energy security, GHG emission reduction, and support to the agriculture.

| Phases | Tasks | Team | Duration | Products |
| --- | --- | --- | --- | --- |
| I |  |  |  |  |
| Based on the knowledge about the Brazilian sugarcane ethanol production model and ethanol production models around the world available in the literature, several possible models will be visualized based on variations of the preliminarily assumed as the optimum model | I.1Workshops on project approach – kick-off I.2 Literature prospecting I.3 Overall data sources prospecting I.4 Choice overall indicators - data prospecting I.5Comparative analyses on agricultural models I.6 Field research in Colombia and Guatemala I.7Analysis on Latin American models’ sustainability indicator I.8 Workshops on project approach – visiting countries feedback | Régis, Posdoc (2) Mauro Berni, Paulo Manduca Beauclair | 2 months 4 months 4 months 1 month 1 month 1 month 2 months 1 month | Data base general |
| II |  |  |  |  |
| 2. Information about the agricultural production model of each country under study will be gathered from the literature and visits to each one and discussions with key representatives of the government, private sector, agricultural workers and NGO’s. The main information to be obtained will be related to the key points: land tenure, size of agricultural properties, level of local capacity, mechanization, main cultures, land productivity levels, and present agricultural practices. This information will complement the data produced by Subproject Regional Diagnosis and the organized information will be used in Phase 3. | II.1Workshops on project approach – team’s feedback workshops on preliminary data II.2 Field research in South Africa and Mozambique II.3 Workshops on project approach – visiting countries feedback II.4 Analysis on African models’ sustainability indicator II.5 Data organization | Régis, Posdoc (2) Mauro Berni, Paulo Manduca Beauclair | 2 months 1 month 1 month 2 months 3 months | Report I Report Workshop |
| III |  |  |  |  |
| All relevant data will be organized in a report such as: forecasted ethanol demand (local market and export), gaps in public policies to introduce or expand the biofuel production, land availability and expected yields, water availability, energy situation, agriculture practices and land tenure profile. | III.1 comparative analysis on regional agricultural models III.2 Analysis on model sustainability indicators III.3 Workshops on project approach – team’s feedback | Régis, Posdoc (2) Mauro Berni, Paulo Manduca Beauclair | 4 month 1 month 1 months | Database on regional models Report II |
| IV |  |  |  |  |
| Alternatives production models will be selected based on the preliminary data and information provided in Phase 3. Each one of these alternatives will favor a key aspect of the sustainability of the production chain, and a tentative to put develop preliminary indicators will be done in order to facilitate the discussion with the different stakeholders. | IV.1 Workshops on project approach – team’s feedback IV.2 Analysis on alternative models IV.3 Analysis on alternative model’s sustainability indicators | Régis, Posdoc (2) Mauro Berni, Paulo Manduca Beauclair | 1 month 1 month 3 month | Database on indicator models Report III |
| V |  |  |  |  |
| Analysis of the alternative and suggestion of the models to be presented to the stakeholders in each country in four specific workshops | V.1 Workshops on project approach – team’s feedback V.2 Workshops on comparative model analysis V.3 Open workshops on final data | Régis, Posdoc (2) Mauro Berni, Paulo Manduca Beauclair | 1.month 1.month 1.month | Report IV |
| VI |  |  |  |  |
| Final analysis and recommendations based of the results of the workshops, and preparation of the final report. | VI. 1 Final considerations VI.2 Preparation final report | Régis, Posdoc (2) Mauro Berni, Paulo Manduca Beauclair | 1 month 1 month | Final report |
| VII |  |  |  |  |
| Publication of articles dealing of the information, findings and recommendations of this sub-project. | VII.1 Sharing knowledge through papers, congress and internet page | Régis, Posdoc (2) Mauro Berni, Paulo Manduca Beauclair | 4 months | papers and essays |

General Choronogram: LACAF-Cane I

Month 2      Month 3                       Month 9    Month 10           Month 12           Month 16         Month 17             Month 18            Month 20  Month 24

↓            ↓                   ↓           ↓                    ↓      ↓                ↓                    ↓                 ↓               ↓

| SP1 Diagnosis (Horta) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SP2a Survey CTC (Beauclair) |  |  |  |  |  |  |  |  |  |
| SP2b Survey Icone (Beauclair) |  |  |  |  |  |  |  |  |  |
| SP2c Determining Land Use and Physical Near-Term Potential (Beauclair) |  |  |  |  |  |  |  |  |  |
| SP3 Productive Model (Regis) |  |  |  |  |  |  |  |  |  |
| Conclusions |  |  |  |  |  |  |  |  |  |

↑              ↑                            ↑               ↑                    ↑                   ↑                     ↑                   ↑                    ↑                 ↑

1st Meeting    2nd Meeting       3rd Meeting          4th Meeting       5th Meeting                   6th Meeting           7th Meeting      8th Meeting

Campinas          Campinas                Calli, CO        Campinas            Durban, AS                                       Campinas               Campinas          Campinas

Professor Titular na FEAGRI/UNICAMP e Vice Reitor de Relações Internacionais da UNICAMP